## Sheet1
Milestone | Task | Subtask | Activity Owner | Owner | Status | ETA | Dependencies | Notes
Pre- Deployment | Schedule Kick Off |  |  | Kathryn | Complete
| Review Linkdin & Salesforce Functionality Overview |  |  | Shawn Nelson | Complete
| Complete Set-Up Salesforce Integration |  |  | Ashish Biswas | Complete
| Review Linkdin Templates |  |  | Shawn Nelson | Complete
Kickoff | Review Deployment Project Plan |  |  | Shawn Nelson | Complete
| Identify Stakeholders |  |  | Shawn Nelson | Complete
| → SF Admin |  |  | Shawn Nelson | Complete
| → Business Sponsor |  |  | Shawn Nelson | Complete
| Set Launch Date |  |  | Shawn Nelson | Complete | 2020-08-14 | Tentetive
| Confirm Use Case(s) & Requirements |  |  | Shawn Nelson | Complete
| Discuss Open Questions |  |  | Kathryn | In Progress | NA | SSO for Mobile
| Schedule Deployment Calls |  |  | Kathryn | Complete
Technical Readiness | Complete Salesforce Integration |  |  | Pramit Kumar | Complete
| → Sandbox Testing |  |  | Pramit Kumar | Complete
| → Connect Linkdin and Salesforce |  |  | Pramit Kumar | Complete
| → Configure Linkdin Document Component |  |  | Pramit Kumar | Complete
| → Embed Associated Document Component |  |  | Pramit Kumar | Complete
| → Automate with Quip Actions |  |  | NA | N/A |  |  |  | N/A
| → Production Configuration |  |  | Pramit Kumar | Complete |  |  |  | Up Coming
| → Connect Quip and Salesforce |  |  | Pramit Kumar | Complete |  |  |  | In Progress
| → Configure Quip Document Component |  |  | Pramit Kumar | Complete |  |  |  | Complete
| → Embed Quip Associated Document Component |  |  | Pramit Kumar | Complete |  |  |  | Delayed
| → Automate with Quip Actions |  |  | NA | N/A |  |  |  | Blocked
| Enable SSO |  |  | Project Lead | In Progress | NA | Partly dependent on salesforce
| → SSO for Web | → CS Assessment → Privacy Assessment → AD Configuration |  | Ashish Biswas | Complete
| → SSO for Mobile | → CS Assessment → Privacy Assessment → AD Configuration |  | Kathryn | In Progress |  | Kathryn / Salesforce
| Determine Domain Accessibility |  |  | Kathryn | Complete
Business Readiness | Finalize Quip Template |  |  | Shawn Nelson | In Progress | 2020-07-20 | After discussed with Ernie
| → Complete Template Consultation / Requirement mapping |  |  | Kathryn | Complete
| Share Folder Structure Best Practices |  |  | Kathryn | Complete
| Identify Pilot Group |  |  | Shawn Nelson | In Progress
| → Provision Pilot Group |  |  | Shawn Nelson | In Progress | 2020-08-20 | After discussion with Ernie.
| Develop Launch Communication Email |  |  | Project Lead | Upcoming
| Determine Enablement Strategy |  |  | Kathryn | Upcoming
Launch Readiness | Open Question Evaluation |  |  | Kathryn | Upcoming
| Send Launch Email |  |  | Project Lead | Upcoming
| Host End User Training |  |  | Project Lead | Upcoming
| Begin Tracking Metrics |  |  | Project Lead | Upcoming
Success Launch | Evaluate Deployment |  |  | Shawn Nelson | Upcoming
| → Consolidate Product Feedback |  |  | Shawn Nelson | Upcoming
| → Discuss Outstanding Items (as needed) |  |  | Shawn Nelson | Upcoming
| Introduce Success Manager |  |  | Shawn Nelson | Upcoming
| Discuss/Celebrate Story Nomination |  |  | Shawn Nelson | Upcoming
| Introduce Deployment Survey |  |  | Shawn Nelson | Upcoming
Solution definition & design | Capture and document user stories for QUIP |  | Business | Shawn Nelson | In Progress | 2020-07-22 |  | Working on capturing user story for WIG template
| Enter user stories in agreed tool ( Agile Accelerator) |  | Business | Shawn Nelson | Complete |  |  | Main user stories completed
| Prioritise user stories for Foundation sprint - Sprint backlog |  | Business | Shawn Nelson | Complete
| Estimate effort per user stories |  | Development | Pramit Kumar | Up Coming
| Translate process flows |  | Development | Pramit Kumar | Complete
| Design model design (Foundation level) |  | Development | Pramit Kumar | Complete
| Define sample data for defined functionality |  | Development | Pramit Kumar | Complete
| Review and confirm sprint plan and designs |  | Business | Shawn Nelson | Complete
Developmen | Schedule show and tells for Foundation Build phase |  | Development | Pramit Kumar | Complete
| Configure user stories for specified accounts |  | Development | Pramit Kumar | Complete
| Configure user stories for specific accounts |  | Development | Pramit Kumar | Complete
| Create and load sample data to test functionality |  | Development | Pramit Kumar | Complete
| Assess technical configuration / development completion against design and user stories |  | Development | Pramit Kumar | Complete
| Release 0 QUIP functionality Sign off |  | Development | NA
Testing | Develop testing strategy including approach and overall timeline |  | SIT | Thumpiri, Sivaiah | Up Coming
| Create and agree structure of testing strategy document |  | SIT | Thumpiri, Sivaiah | Up Coming
| Define test scenarios for Foundation Sprint |  | SIT | Thumpiri, Sivaiah | Up Coming
DELIVERABLE: Testing Strategy (Approach & Timeline)
| Develop test scripts for UAT |  | SIT | NA | Up Coming
| Develop test scripts for SIT |  | SIT | NA | Up Coming
| Sign off Test Scripts |  | Business | NA | Up Coming
EXECUTION | Confirm testing logistics and set-up requirements (SIT / Performance Testing) |  | SIT | Thumpiri, Sivaiah | Complete
| Confirm testing group requirements for UAT (number and locations of users) |  | SIT | Thumpiri, Sivaiah | Complete
| Schedule relevant testing sessions |  | SIT | Thumpiri, Sivaiah | Complete
| Test workspace and access |  | SIT | Thumpiri, Sivaiah | Complete
| Perform SIT |  | SIT | Thumpiri, Sivaiah | Complete
| Remediate SIT issues |  | SIT | Thumpiri, Sivaiah | Complete
| Document SIT results |  | SIT | Thumpiri, Sivaiah | Complete
| Sign off on SIT Results |  | SIT | Thumpiri, Sivaiah | Complete
| Test configuration against test cases (UAT) |  | Business | Shawn Nelson | Complete |  |  | I think this was completed "Shawn"
| Remediate UAT Issues |  | Business | Shawn Nelson | Complete
| Validate UAT issues resolved |  | Business | Shawn Nelson | Complete
| Document UAT results |  | Business | Shawn Nelson | Complete
| Sign off on UAT results |  | Business | Shawn Nelson | Complete
DELIVERABLE: Testing Outcomes Summary / Go Live Readiness
Go Live | Gain approval against go / no go criteria for release 1 |  | Business | Shawn Nelson | Complete
| Complete cutover / launch activities (i.e. access provision, Concur instance activation) |  | Business | Shawn Nelson | In Progress | 2020-08-03
| DELIVERABLE: Go Live for release 1 |  |  | Shawn Nelson | Up Coming | 2020-08-10
| Gain approval against go / no go criteria |  | Business | Shawn Nelson | Up Coming | ?
| Complete cutover / launch activities (i.e. access provision, Concur instance activation) |  | Business | Shawn Nelson | Up Coming | ?
DELIVERABLE: Go Live for release 2