## Sheet1
WinZone 2022 Release Calendar
[6 empty] | Release related Important Dates |  |  | Sprints dates involved in each month's Release |  |  |  | DownStream Systems Release dates
Sl. No. | Month | Planned Release Dates | Actual release Dates | Justification for Change | Key Impacting Dates | SIT Freeze | Code Freeze | Go NO GO | Sprint 1 dates | Sprint 2 dates | Sprint 3 dates | Infra- GCCB, DR | CRS | ESA | Cforecast
1 | Jan | 2022-01-22 | 2022-01-22 | NA | 14 Jan- Bangalore, Chennai 26-Jan- Republic Day All Location | 2022-01-14 | 2022-01-18 | 2022-01-19 | Sprint 42 (Nov 29-Dec 10) | Sprint 43 (Dec 13-Dec 24) | Sprint 44 (Dec 27-Jan 07) | Jan 17th (GCCB) | NA | NA
2 | Feb | 2022-02-19 | 2022-02-19 | NA |  | 2022-02-11 | 2022-02-15 | 2022-02-16 | Sprint 45 (Jan 10th-Jan 21st) | Sprint 46 (Jan 24th –Feb 04th) |  | Feb 21st (GCCB) | NA | NA | 2nd -15th
3 | Mar | 2022-03-12 | 2022-03-12 | NA | 1st March -Mahashivaratri 18th March- Holi | 2022-03-04 | 2022-03-08 | 2022-03-09 | Sprint 47(Feb 7th-Feb 18th ) | Sprint 48 (Feb 21st- Mar 4th) |  | Mar 21st GCCB, DR date- Mar 27th - Mar 28th | NA | NA | 2nd -15th
4 | Apr | 2022-04-16 | 2022-04-16 | NA | 15th April- Good Friday/Bengali New year | 2022-04-08 | 2022-04-12 | 2022-04-13 | Sprint 49 (Mar 7th –Mar 18th ) | Sprint 50 (Mar 21st- Apr 1st ) |  | Apr 18th (GCCB) | NA | NA | 2nd -15th
5 | May | 2022-05-21 | 2022-05-21 | NA | 03-May : Ramzan (Id-ul-Fitr) - Regional Holiday in Kolkata, Bangalore | 2022-05-13 | 2022-05-17 | 2022-05-18 | Sprint 51 (Apr 4th- Apr 15th ) | Sprint 52 ( Apr 18th- Apr 29th) | Sprint 53 ( May 2nd –May 13th) | May 16th (GCCB) | NA | NA | 2nd -15th
6 | Jun | 2022-06-18 | 2022-06-18 | NA |  | 2022-06-10 | 2022-06-14 | 2022-06-15 | Sprint 54 (May 16th- May 27th) | Sprint 55 (May 30th- June 10th) |  | June 20th (GCCB) | NA | NA | 2nd -15th
7 | Jul | 2022-07-16 | 2022-07-16 | NA |  | 2022-07-08 | 2022-07-12 | 2022-07-13 | Sprint 56(June 13th-June 24th) | Sprint 57(June 27th-July 8th) |  | July 18th (GCCB) | NA | NA | 2nd -15th
8 | Aug | 2022-08-20 | 2022-08-20 | NA | 15 Aug- Independence day 19 Aug-Janamastmi 31 Aug Ganesh Chaturthi | 2022-08-12 | 2022-08-16 | 2022-08-17 | Sprint 58 (July 11th- July 22nd) | Sprint 59 (July 25th- Aug 05th) |  | Aug 22nd (GCCB) | NA | NA | 2nd -15th
9 | Sep | 2022-09-17 | 2022-09-17 | NA | 07th Sep- Regional Holiday South India | 2022-09-09 | 2022-09-13 | 2022-09-14 | Sprint 60 (Aug 08th-Aug 19th) | Sprint 61 (Aug 22nd- Sep 02nd) |  | Sept 19th (GCCB) | NA | NA | 2nd -15th
10 | Oct | 2022-10-15 | 2022-10-15 | NA | 3,4,5 Oct- Durga Puja festival and Dussera 24th,25th Oct-Diwali | 2022-10-07 | 2022-10-11 | 2022-10-12 | Sprint 62 (Sep 5th-Sep 16th) | Sprint 63 (Sep 19th- Sep 30th) |  | Oct 17th (GCCB) | NA | NA | 2nd -15th
11 | Nov | 2022-11-19 | 2022-11-19 | NA |  | 2022-11-11 | 2022-11-15 | 2022-11-16 | Sprint 64 (Oct 03rd-Oct 14th) | Sprint 65 (Oct 17th- Oct 28th) |  | Nov 21st (GCCB) | NA | NA | 2nd -15th
12 | Dec | 2022-12-10 | 2022-12-10 | NA |  | 2022-12-02 | 2022-12-06 | 2022-12-07 | Sprint 66 (Oct 31st-Nov 11th) | Sprint 67 (Nov 14th- Nov 25th) | Sprint 68 (Nov 28th- Dec 02nd) | Dec 19th (GCCB) | NA | NA | 2nd -15th
Note:
December release depends on the freeze dates.
Releases falling under cforecast cycle there should not be any dependent workitem planned for that release related to cforecast, we may need to reconsider the timelines depending on the prioritization.