## Sheet1
Sprint planning Template
Capacity Calculation (only Parented work) | [6 empty] | Adds business value
Team Member |  | Initial Story Points | Holidays/ PTO | Capacity per sprint (SP) | Load per sprint - 85% of capacity (SP) |  | (85% planned) | (15% Buffer) - unparented tasks
| Allocation % | [5 empty] | Exploratory | Learning/Certification
|  |  |  | 100% | 85% |  | User stories | Skip level meet
Pramit Kumar | 100% | 8 | 1 | 7 | 5.95 |  | Scope addition | GoPerform
Org. initiatives
[7 empty] | No. of participants (Eg.) | 3 members |  |  |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
[7 empty] | Avg. velocity | 50 SP |  |  | story 1 | 3 | 5 | 5 | 2 | 1
[7 empty] | Feature |  |  |  | story 2 | 5 | 3 | 5 | 3 | 3
[7 empty] | S | 1 sprint (3 weeks) | 50SP | Recommended | story 3 | 5 | 5 | 3 | 3 | 3
[7 empty] | M | 2 sprints (6) - 1.2 months | 100 SP | Recommended | story 4 | 5 | 5 | 5 | 5 | 3
[7 empty] | L | 3 sprints (9) - 2.2 months | 150 SP | Large feature | story 5 |  |  |  | 5 | 3
[7 empty] | XL | 4 sprints (12) - 3 months | 200 SP | Large feature | story 6 |  |  |  |  | 5
|  |  | Total | 7 | 5.95 | Velocity |  |  |  |  | Velocity | 18 | 18 | 18 | 18 | 18
[11 empty] | Throughput | 4 | 4 | 4 | 5 | 6
85%
4
Enter Sprint Length(weeks) | 2
Per person (max. hrs in a sprint) | 90 | [6 empty] | 14.875 | 2.2312 | 12.6438
Initial Story Points | 10 | 1 day = 1 SP |  | 1,2,3,5,8,13,20,40….
backlog grooming (5-10% effort) | 4.5 | 5-10% of devteam efforts in a sprint
sprint planning (hrs) | 4 | 2 hrs every 1 week sprint | [6 empty] | Dev | QA
review (hrs) | 2 | 1 hr every 1 week sprint | [5 empty] | US1 | 6 | 2
retro (hrs) | 1.5 | 45mins. Every 1 week sprint
Daily Scrum | 10 | 1 Hr. Everyday
Total hrs. spent | 22
Total storypoints to be deducted 1 day = 1 SP | 2.4444
Initial Story Points | 7.5556
Timeboxing Events
https://resources.scrumalliance.org/Article/scrum-events#:~:text=Scrum%20defines%20four%20events%20(sometimes,sprint%20review%2C%20and%20sprint%20retrospective.
Backlog refinement
https://www.scrum.org/resources/blog/scrum-trenches-product-backlog-refinement-scrum-team-responsibility?gclid=Cj0KCQjw4v2EBhCtARIsACan3nxSsrovH-jIpqalwOUTXOMnXz643x3C3gqq8WC_eVn24M3XUzm9Kw4aArsDEALw_wcB
https://www.mountaingoatsoftware.com/blog/backlog-grooming-who-should-attend-and-how-to-maximize-value

## Sheet2
Sprint 48
Developer | Day Capacity | Available days | Sprint Capacity
Akarsh | 0.4 | 10 | 4
Pramit | 0.8 | 10 | 8
Moumita | 0.4 | 10 | 4
Nagaraj | 0.8 | 10 | 8
Kavya | 0.8 | 10 | 8
R1 | 0.8 | 10 | 8
Indranil | 0.8 | 10 | 8
Shwet | 0.8 | 10 | 8
R4 | 0.8 | 10 | 8
Total |  |  | 64
160